## Sheet1
Task | Start Date | Days Allocated to complete | status | Members who worked on task | Extention required
Basic information collection(Location / Family energy consumption / equipment energy consumption) | 2019-04-28 | 3 | Complete | VINCENT,KURTIS,ELIJAH ,ISAAC ,PALDEN,AHAN | No
Energy consumption and solar requirement calculation | 2019-04-29 | 1 | Complete | AHAN | No
Gantt Chart | 2019-04-29 | 1 | Complete | AHAN | No
Number of batteries and accessories required | 2019-04-29 | 1 | Complete | VINCENT | No
Micro-Grid sketches and Satellite image representation | 2019-04-30 | 10 | Complete | VINCENT | No
CAD Models of Equipment | 2019-05-05 | 5 | Complete | VINCENT | No
General Microgrid description | 2019-05-01 | 1 | Complete | AHAN | No
Solar Panel Description | 2019-05-01 | 2 | Complete | AHAN | No
Solar panel critical points and comparison | 2019-05-01 | 2 | Complete | KURTIS | No
Electric fence description | 2019-05-03 | 2 | Complete | AHAN | No
Electric fence Critical points and comparison | 2019-05-03 | 2 | Complete | PALDEN | No
Inverter description | 2019-05-03 | 2 | Complete | AHAN | No
Inverter critical points and comparison | 2019-05-03 | 2 | Complete | AHAN | No
Storage Battery Unit Description | 2019-05-03 | 2 | Complete | ISAAC | No
Battery Unit Critical points and description | 2019-05-03 | 2 | Complete | ELIJAH | No
Cow brush description | 2019-05-03 | 2 | Complete | PALDEN | No
Final micro grid description | 2019-05-05 | 2 | Complete | AHAN | No
Compiling Initial report | 2019-05-07 | 3 | Complete | AHAN | No
Editting final report | 2019-05-10 | 1 | Complete | VINCENT | No